###### Parking Services

###### Business Plan 2006/07

Contents:

1.	Background

2.	Introduction to Department – setting the scene

3.	Performance and achievements

4.	People and resources

5.	Key service priorities 2006/07 and risk management

6. 	Equality and Diversity

7.	Monitoring and review

###### 1.	Background

  - Efficient transport provision within the City is vital to the economy and quality of life of everybody concerned. As a regulatory service, Parking Services is a significant contributor to the maintenance of order on the highway. Within the City of Westminster, effective control of parking is essential in combating the negative effects of parking; traffic congestion, illegal parking, obstructions etc. This plan outlines the challenges ahead for Parking Services for 2006/07.

  - Westminster's Parking Service is the largest in Europe by way of PCN issue but also by the number of visitors, businesses and residents the council has to provide for. This provides a significant challenge in balancing the requirements of each. It has an income of approaching £85m with costs of over £57m, the remaining surplus is used to fund other Transportation related projects including bridges, taxi-cards and bus-passes.

  - The service is responsible for providing and managing on and off-street parking services, enforcing on-street parking controls throughout Westminster. It does this with a client team of 42 staff managing over 750 sub-contracted staff through a number of contracts.

  - The on-street service comprises installation and maintenance of lines, signs, meters and pay and display machines, patrolling the streets and enforcing the parking regulations through the issue of penalty charge notices (PCNs), and clamping and removal of illegally parked vehicles. In addition it is responsible for managing permissions and suspensions of its on-street space.

  - Off-street, Westminster operates 17 car parks across the borough, managing their marketing, pricing, management and maintenance and development.

  - Parking Services forms part of the Central Services Department of the Council. Parking reports to the Cabinet Member for Economic Development and Transportation and hence is closely linked to the Transportation Department on matters relating to transport and parking policy, highway maintenance and planning issues.

  - The service has made considerable improvements in its policy, performance and service delivery in the last 18 months. The implementation of a new computer system called ICPS in April 2005 has underpinned the re-engineering of the back office processes, improved PCN quality and provided key management information.  It is on this growing basis of understanding that the service has stabilised and will continue to improve against key performance metrics set out in this document.

2.	Introduction to Parking Services

  - Mission Statement:  To efficiently and effectively manage the kerbside and off-street space in Westminster for our customers and stakeholders in a firm yet fair manner and in doing so become recognised as the best parking service in the UK by the end of 2006

  - Key resources provided or managed by the Parking Service:

- 37,000 residents Permits

  - 32,000 spaces

- 8,000 metered spaces

  - 700 P&D’s – covering 3,500 spaces

  - 4,500 meters

- 5,500 off street spaces

- 5,500 Westminster Disabled Parking Permits

- 20,000 tradesman permits

- 14,000 suspensions per annum

- 6,000 other permits and permissions to park

- 1,600 annual Car Park season tickets

  - Top level statistics of the enforcement service

- c715,000PCNs (expected FY 05/06)

  - 14,000 clamps and

  - 19,000 removals

- c36,000 Resident Permits on-issue

- 665,000 Telephone calls

- 227,000 enquiries

- 332,000 payments

- 106,000 other telephone calls

- 179,000 informal challenges

- 82,000 formal challenges

- 13,000 Appeals to Parking Adjudicator

  - Success rate c60% (of contested appeals)

  - Summary of available resources

- On-street c450 staff

- Back-office & telephony c300 staff

- Client management – 42 staff

- Three One Stop Shops

  - 85% of activities are parking related

- Off Street - 17 Master Park car parks

- Significant partnerships - NCP, Vertex, APT, Accord

  - Financial Summary

|  | 2004/05 Actual | 2005/Revised Budget | 2006/07 Target |
| --- | --- | --- | --- |
| Income |  |  |  |
| On-Street | £72.2M | £65.4M | £70.5M |
| Off-Street* | £34.7M | £20.2M | £19.8M |
| Expenditure |  |  |  |
| On-Street | £39.7M | £40.5M | £38.6M |
| Off-Street | £20.6M | £16.7M | £16.6M |
| Surplus |  |  |  |
| On-Street | £32.5M | £24.9M | £31.9M |
| Off-Street | £14.1M | £3.5M | £3.2M |

* Note variance in income is due to change in treatment of PPRA contributions

  - Challenges;

- Enforcing Central London

- Need to balance demands for Kerbside space

- Loading / unloading - complex issues / complex rules / not understood

- 24 hour City - difficulties enforcing at night

- Perception of over enforcement - CCTV, speed cameras

- Congestion Charge & western extension

- Cross-rail

- Negative media coverage

- High cost to serve

- Poor customer perception - not easy to do business with

  - Service aims

- To reduce congestion, provide parking space for essential users and raise compliance with parking regulations, as set out in the Mayor’s Transport Strategy and the City Council Unitary Development Plan.

- To enforce efficiently, effectively and fairly the kerbside space by ensuring the right policy and processes are in place and that our partners are managed appropriately to deliver against the service goals.

- To offer Westminster customers an appropriate on-street and off-street pre or post pay parking facility and deliver WCC’s financial targets and maximising asset return.

- To lead the development and deployment of technology and processes that will make WCC easier to do business with for our customers and contractors and significantly reduce cost or boost revenue.

- To gather and maintain an accurate customer and internal view of WCC’s parking service and represent this view to all internal parties within the organisation to stimulate positive change.

- To manage the Parking Unit effectively and efficiently, developing staff and ensuring the Unit is ‘joined-up’ to the rest of the Council and its activities.

- To provide widespread visibility of the Parking Unit’s financial position by developing, maintaining and disseminating an agreed set of financial and process measurements whilst exercising tight financial control.

- To be at the forefront of the development and implementation of new and relevant parking initiatives.

- Work in close cooperation with other local Authorities, particularly neighbouring ones, and also with related agencies including the DVLA, Transport for London, DfT and Police.

- Promote best practice and continual quality improvement across the service and within the parking industry as a whole.

3.	Performance and Achievements

  - This section reviews the Parking Service’s current performance against targets and customer expectations during 2005/06.

How the service met its objectives – 2005/06

  - Departmental performance against key targets, standards and indicators in 2005/06

| Key Performance Indicator (KPI) | 2004/05 Actual | 2005/06 Budget | 2005/06 Forecast | 2006/07 Target |
| --- | --- | --- | --- | --- |
| On-Street Enforcement |  |  |  |  |
| PCN Issued | 817,000 | 906,000 | 715,000 | 746,000 |
| Productivity (tickets / hour) | 1.58 | 1.64 | 1.33 | 1.5 |
| PCNs cancelled (Contractor.PA Error) | 1.5% | 0.5% | 1% | 0.5% |
| Clamps (number / week) | 913 | 229 | 265 | 300 |
| Clamps per hour | 0.85 | - | - | 1 |
| Removals (number / week) | 254 | 217 | 360 | 360 |
| Removals per hour | 0.49 | - | 0.6 | 0.7 |
| Code reds & yellows (% reduction on previous year) | - | - | - | 20% |
| PCN Payments |  |  |  |  |
| PCN’s Paid (%) | 73% | 74% | 70% * | 72% * |
| Average Value (£) | 60.24 | £60 | £64 * | £64 * |
|  |  |  | * TBC |  |
| Correspondence |  |  |  |  |
| Incoming correspondence (% per PCN) | 25% | 25% | 25% | 20% |
| Response times (days) Pre NtO Challenges | - | 10 | 10 | 5 |
| Response Times Post NtO Representations | - | 20 | 10 | 5 |
| Cancellation rate (as a % of challenged) | 39% | - | 40% | 35% |
| Appeals |  |  |  |  |
| Volume (number) | 11,222 | - | - | - |
| Won (%) | 54% | - | - | - |
| DNC (%) | 23% | - | 15% | 15% |
| Complaints |  |  |  |  |
| Upheld | 124 | - | - | - |
| Partially Upheld | 54 | - | - | - |
| Not Upheld | 700 | - | - | - |
| Turnaround (days) | 20 | 20 | 20 | 10 |
| Telephony |  |  |  |  |
| Enquiry Calls Offered (number / month) | 16,700 | 16,700 | 16,600 | 16,700 |
| Payment Calls offered (number / month) | 18,800 | 18,800 | 10,000 | 18,800 |
| Total calls answered in SLA (80/20) | 88% | 80% | 91% | 80% |
| Off Street |  |  |  |  |
| Utilisation % |  |  | 50 |  |
| Season Tickets Sold (number) |  | 1600 | 1600 |  |

- The department is not assessed against any BVPIs or other national indicators nor is measured against any key local performance indicators or LPSA stretch targets.

- The Service does compare itself against other boroughs, particularly those in Central London via the ALG TEC. Details of this comparison including ticket issue volumes and appeal data can be found via www.alg.gov.uk.

  - Understanding customer expectations.

At the end of 2004 the Parking Service undertook a survey to understand users expectations and perceptions of the service in Westminster.  The results of this survey have initiated a number of initiatives and have been used to address policy and communication issues throughout the 2005/06 year.

The survey was undertaken in 2 parts;

- Quantitative - 1200 people were interviewed and,

- Qualitative - focus groups, personal in-depth and structured interviews with residents, businesses and visitors.

The key findings were;

- The overall perception of Parking Attendants is negative.

People feel our service has no personality or that we have paid particular attention to their case and investigated it properly.

- Parking Customers are requesting flexible options to pay for their parking; Cashless parking, Oystercard, using a mobile phone and paying by credit/debit card at parking meters.

- Nearly ¾ of businesses feel that there is unfair enforcement of loading and unloading regulations by Parking Attendants but also there is only a superficial understanding of protocols by commercial drivers.

- Cheques are the preferred option to pay for parking fines.  Customers were generally unaware of the other payments methods available.

  - Addressing the issues.

During the 2005/06 year a number of activities were initiated to address the key issues.

- The Parking Charter was launched and made available on the web

- The enforcement protocol was published on the web and publicised

- The Freedom of Information Act was introduced

- Loading DVD was produced, launched and circulated

- Letter correspondence has been quality monitored and simplified

- Digital cameras and updated handhelds were provided to NCP staff in conjunction with a new computer system and processes

- NCP long stayer workshops were held to investigate behaviours and changes made to their training and induction programmes

- Significant increase in positive communication opportunities in press, radio and TV.

- A programme of quality improvement for communications is on going

- A cash-less, debit and credit card, payment project is in trial in 21 pay and display machines

In addition, some parking policies have been simplified to increase understanding and compliance with the regulations.

- Motorists are now allowed to ‘feed’ meters up to the maximum stay duration.

- The clamp service has been re-based to reduce the volume of clamps significantly.

- Respark criteria have been eased for renewal customers, copies now accepted, online soon.

- Maximum stay durations have been increased from 2 hours to 4 hours on the majority of meters and P&D machines in Westminster.

- A number of parking bays have been re-designated as residents only or mixed use (residents and P&D).  This has increased the ratio of permits to spaces to 97% across Westminster.

- Promoted best practice and ensured consultation with key opinion formers.

  - Planned activities and outcomes 2005/06.

| Project | Objective | Status |
| --- | --- | --- |
| ENFORCEMENT |  |  |
| Parking Charter | - Actively communicate the enforcement regime in a way that customers can understand and have free access to e.g. Web | Complete |
| Deliver & secure TOPS Phase I | - Implement new IT and business process for Parking ensuring all expected benefits are fully realised. - Specified in TOPS service promises document. | Complete |
| End to End Quality | - Create a virtuous circle of quality improvement through NCP, Vertex and WCC. Once concluded all will understand the cost of each policy and process the volume of revenue that flows through each and the cost or opportunity of each type of PCN by offence and location. | Complete |
| On-street NCP contract review | - Bring the on-street enforcement contract up to date to incentivise quality and provide more robust and proactive monitoring, fixed and variable costs, supervision rates and contractor margins. | New enforcement model being developed |
| PA Development | - Develop and implement a plan with NCP to improve PA retention beyond 1 year by providing education, development & customer service skills possibly resulting in an NVQ with pay increase and an increase in average tenure from 12 months to 15 months. | Partially completed (due for completion Q4 05/06) |
| Dynamic NCP contract management | - To drive the delivery of the on-street enforcement service to proactive and responsive. Test the concept of a PA ‘SWAT’ team to test what is possible in an area. - Reduce supervisor ratio from 1:6 – 1.8. | Still being developed |
| Data/Photo quality programme | - Announce photo evidence based on-street enforcement, keep image/offence ratio >90% and drive quality. | Complete |
| Vertex Contract | - Ensure Vertex contract fits with NCP and WCC goals. - Make sure all stakeholders understand contract make up and proper change control procedure exists. | Still being developed |
| Lower cost of payment | - Reduce cost of payment process for all channels. | Not achieved |
| Protocol review | - Deliver the best on-street protocols to ensure that they reflect parking and traffic management needs and communicate widely. - Empower NCP to join with Police & DVLA to tackle head-on unlicensed mini cab invasion. | Complete |
| TOPS Phase 2 | - Define and implement enhancements to TOPS to improve service delivery. - Cut 10% of back-office management costs by adding critical TOPS modules. | Some elements completed others deleted on review of priorities |
| CCTV Implementation and roll out | - Deliver CCTV enforcement of bus lanes and explore opportunities for its roll out. - Over achieve CCTV target by 100%. | Complete |
| KERBSIDE SPACE |  |  |
| Kerbside strategy | - Develop and agree longer term kerbside strategy – to include consideration of yield management, automatic street presence awareness and joined-up thinking with off-street | Some elements completed |
| Residents Parking | - Cut 50% of the cost and complexity of the process by removing need to produce all proofs each year and visit One Stop. | Complete |
| Disabled Parking | - Simplify and improve security of the application Occupational Therapist (OT) assessment process | Not achieved |
| Provision and control of spaces via Area Parking Studies | - Review existing controls and the provision and distribution of parking spaces on street. - Ongoing programme. | Not achieved |
| On-street equipment supply and maintenance contract re-let | - Provide reliable & secure equipment that provides motorists with varied payment options, improves income collection and reduces theft as well as maintenance costs, to include chip and pin pay and display and mobile payment options. - By end of 2005/06 financial year we have replaced 50% of meter space with new P&D machines and 50% of kerbside revenue is cashless. | Partially achieved |
| OFF-STREET |  |  |
| Develop off-street strategy | - Develop a robust and independent assessment for the future of the business to inform the tender evaluation and the preferred way forward | Complete |
| Define and execute sales & Marketing programme | - Prepare Sales and Marketing programme for 05/06 | Complete |
| Manage Re-let process | - Manage and monitor the re-let process to ensure the City Council procures the most economically advantageous contract | Complete |
| CUSTOMER EXPERIENCE |  |  |
| Customer research | - Implement a customer research programme to identify our customers’ needs and prioritise our actions and decisions based on them | Complete |
| Parking extranet site | - Support the resolution of customer enquiries and to act as an internal communication tool. | Complete |
| Quality Management | - Significantly improve the quality of correspondence with our customers. | Partially Complete |
| Communication | - Improve communication internally between Westminster, NCP and Vertex and via external measures to our customers (for example the web). | Complete |
| MANAGEMENT & FINANCE |  |  |
| BETTER WORKING Reorganisation | - Substantively complete reorganisation | Complete |
| Optimise office space | - Reduce the amount of office space (and cost) used by Parking on 10th Floor, City Hall by 30% | Complete |
| Remote/flexible working | - Remote or home working will be supported and encouraged, to allow staff to get closer to the customer and contractor | Complete |
| BETTER ACCOUNTABILITY Performance Review | - Team know everyone’s accountabilities and take responsibility for delivering their objectives | Complete |
| Define and maintain KPI pack and deliver MI to accountable managers | - Agree key performance measures and indicators for all key services. - Develop and define strategic MI needed to support the effective management of the business. | Partially Complete |
| BETTER SUPPORT Visibility and integration of Parking Unit | - Parking is recognised as a key contributor to the Council’s corporate provision. | Complete |
| Team training and development | - Training programme for all staff that develops key skills, provides opportunity for development and rewards talent. Demonstrated through IIP accreditation. | In progress, pursuing IIP accreditation 2006/7 |
| Strengthen external linkages | - To position CoW parking as a leader and driving force in the London and UK parking industry. | Complete and on-going |
| Increase the debt recovery rate | - Increase the debt recovery rate from 71% to 74% through improvements in the recovery process and the use of debtor information. - Look for opportunities to stretch to 76%. | DCU agreement in place |

Details correct to end Q3 2005.

- People and resources

  - 2005/06 has been a transition year for the Parking Service.  The new service structure which was agreed at the end of 2004/05 has been implemented during this year.  A further re-structure was also implemented during the last quarter of 2004/05, in addition a significant reduction in utilised office space (and cost) has been made with the introduction of remote working capabilities for most staff.

This is now complete and at present there are no foreseen demands which would make further restructuring necessary. The breakdown of staff numbers within the client management team is;

|  | 2005/06 Actual | 2006/07 Budget |
| --- | --- | --- |
| Management & Administrative | 4 | 4 |
| Policy & Compliance | 13 | 12 |
| Car Parks | 10 | 4 |
| Infrastructure | 4 | 5 |
| Service Development | 5 | 6 |
| Finance | 8 | 7 |
| Customer Experience | 4 | 4 |
| Total | 48 | 42 |

  - Remote / Flexible working

During 2005/06 the parking service implemented a remote/home working policy.  This enabled the releasing of over 18 desk spaces on the 10th Floor of City Hall.

A number of lessons have been learned from the experiences of the Parking service during this transition which will be passed onto other departments considering the same.

  - Recruitment / Retention

The service has been subject to two reorganisations during the last two years which has resulted in a reduction of 6 posts.  It is unlikely that the service will face any staff retention issue throughout the year as a large number of staff are new to the organisation.

The service has successfully used online recruitment and a contracted recruitment manager to run the recruitment process, opted out of expensive press advertising.

The department has no obvious staff recruitment or retention issues.

  - Skills & Knowledge

The service is holding a series of staff workshops during February 2006 to inform and encourage officers to take an active role in their learning and development using the City Council’s on-line tools and competency framework.  Following the implementation of the recent re-organisation, officers within Infrastructure and Policy & Compliance Teams will receive specific training around the off-street operation as they will take responsibility for the management of this service and the new contract arrangements.

  - Staff Consultation

Each member of staff has a regular one to one meeting with their line manager and teams have monthly meetings to discuss current issues and concerns.  Management have a healthy working relationship with the Union and hold quarterly meetings with the local shop steward to discuss any specific concerns.

In addition, senior managers brief staff on a quarterly basis on progress against specific business planning targets.  Information is available to staff on Parking’s extranet site which is shared with our partners, Vertex and NCP.

Parking has established a staff charter, agreed by staff and management which both work to.

- Key Service Priorities 2006/07 and Risk Management

  - Departmental priorities overview

The Parking Service will continue to demonstrate a service that strives to be consistent and fair in enforcing our duties, whilst making things simpler and easier for our customers. It will do this by observing the following priorities:

    - The on-going development and improvement of TOPS (the Parking Service IT system) gives us the platform to much better and more timely management information to develop new applications, better processes and hence cut costs.

    - Supporting Vertex in the relocation of services to the Dingwall call centre using the opportunity to improve our services.

    - Following the successful implementation of a simplified Residents Permit renewal process, a review of the entire permit strategy will be undertaken for the other 30 plus permits, currently in use in Westminster, with the aim to make everyone’s life easier, cut costs and complexity from the varied processes.

    - Continuing the roll-out of our car parks management strategy with our chosen partner CPS.  Also we will develop the strength of our sales and marketing efforts to maximise the revenue potential of the car parks.

    - Continuing to push the Parking Charter and communicating the enforcement rules in a clear and consistent manner.

    - Continuing to develop and lead the ‘Partnerships in Parking’ programme with other London boroughs, with the aim of developing a consistent set of standards which can be adopted across London to make parking easier to understand for Londoner’s or visitors to London as a whole.

    - Improving our own knowledge of our customers and their needs and perpetuate this influence internally.

  - Key Initiatives overview  (See Appendix 3 for detail)

Enforcement

1. CCTV enforcement

2. EffectiveOn-Street Enforcement

3. Effective back-office

Kerbside

4. On-Street Equipment

5. Partnerships in Parking

6. Permits & dispensations

7. Suspensions

Offstreet

8. Off-Street

Customer Experience

9. Internal view

10. External view

Team Management

11. Staff Development

  - Risk Management

See appendix 3 for current department risk register.

6.     	Equalities and Diversity

6.1	Parking administers a number of statutory processes involving disability regulations, particularly the blue and white badge parking permit schemes. Also it is required to provide DDA compliant customer facilities, especially car parks on on-street spaces. The department will endeavour to comply with all statutory requirements in this area whilst balancing the constant and often competing demand for space and facilities on and off-street.

6.2	From the point of view of ensuring equality both within its workforce and to its customers, the Parking Unit will ensure that staff are trained in equality issues and practices, develop an equality plan and ensure that regular audits are carried out to monitor compliance. This work will be lead by the Customer Experience team within the unit.

6.3	The Parking client will also ensure that its approach to enforcement is balanced and fair and that its rules are considered on a community by community basis as well as Council-wide.

6.4	In relation to its employees, including sub-contractor staff, the Parking Unit will vigorously defend and protect the diversity of staff within the team from verbal or physical abuse from members of the public, including pressing for criminal prosecution where appropriate.

7.	Business Plan Monitoring and Review

  - See Appendix 2 for Monitoring proposals for each key initiative.

8	Financial Summary

8.1	See Appendix 1.

Appendix 2: Departmental Priorities 2006/07

| Objective | Planned actions | Timescales and milestones | Lead (desirable) | Targeted outcome | Resources | Reporting arrangements and frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Enforcement |  |  |  |  |  |  |
| 1. CCTV enforcement | 1.1 Roll-out additional cameras for Moving Traffic Contravention enforcement | Q4 2007 | Service Development | Introduce enforcement on 50 WCCT cameras |  | Quarterly to Overview & Scrutiny Committee |
|  | 1.2 Implement stationary contravention enforcement | Q4 2007 |  | 5% of all stationary PCN’s issued by CCTV in final quarter of year |  | Quarterly to Overview & Scrutiny Committee |
|  | 1.3 Implement night enforcement | Q2 2006 |  | Introduce enforcement from 10pm to 2am in the West End. Target 2000 PCN’s issued by end of year |  | Quarterly to Overview & Scrutiny Committee |
|  | 1.4 Implement other new CCTV technologies (e.g. Smart Cars, Automated tracking software) | Q4 2006 |  | Gain authority from ALG-TEC to utilise different technologies for enforcement and test deploy. |  | Quarterly to Overview & Scrutiny Committee |
|  | 1.5 Roll-out Wireless City Phase 1B (Subject to Business Case being proven by pilot) | Q3 2006 |  | Implement additional 5 Wireless moveable cameras (subject to the wireless network being available) |  | Quarterly to Overview & Scrutiny Committee |

| 2. Effective On-Street Enforcement | 2.1 On-going review & Improvement Targeting resources by area, by time of day and by day of week | Q4 2006 | Policy & Compliance Team | - 746,000 PCNs in 2006/07 - Less than ½% of PCNs are cancelled due to Parking Attendant error - A 20% efficiency gain in unit cost per PCN issued | Policy and Compliance NCP MI Manager | Quarterly to Overview & Scrutiny Committee |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2.2 Persistent Evaders | Q2 2006 | Policy & Compliance Team | Cross-borough PE list and processes established. Secondary enforcement and back office processes developed for PEs. Commence proactive tracing in back office with Bailiff support | Policy & Compliance NCP Vertex | Quarterly to Overview & Scrutiny Committee |

| Objective | Planned actions | Timescales and milestones | Lead (desirable) | Targeted outcome | Resources | Reporting arrangements and frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Enforcement continued |  |  |  |  |  |  |
|  | 2.3 Digital Images on the Web | Q2 2006 | Policy & Compliance | Provide customers access to the images we capture of their contraventions - 100% of images held in ICPS on web (Q1) - 90% quality of images on web (Q2) | IT Service Development Legal | Quarterly to Overview & Scrutiny Committee |
|  | 2.4 Develop strategy and prepare for on-street contract re-let in 2007 | Q4 2007 | Policy & Compliance | Approval of strategy | Policy & Compliance | Cabinet Report Only |
|  | 2.5 Investigate opportunities to ‘sell’ our expertise into other areas | Q3 2006 | Policy & Compliance | Explore additional enforcement opportunities: DVLA, TfL (Q1), Red Routes Consultancy Strategy for Parking Services | Policy & Compliance Legal Vertex | Quarterly to Overview & Scrutiny Committee |

| 3. Effective back-office | 3.1 Develop and deliver Management Information Dashboard | Q1 2006 Implement (Q2 review) | Management Information Manager | Review current strategic monitoring. Develop an effective MI tool for monitoring the new incentives model to be introduced from 1 April 06. Clear and concise measures to meet business expectations. | Policy & Compliance Team | Weekly Parking Managers Operation Meeting |
| --- | --- | --- | --- | --- | --- | --- |
|  | 3.2 Debt Collection Unit | Q4 2007 | Parking Finance | Build on the trial Debt Collection Unit established in Q4 05/06 to drive payment rate up by 1.5% points in FY 06/07 and 1 percentage point in FY 07/08 whilst maintaining the average value per PCN at £64 or above. | Finance Service Development | Monthly to Parking Board and Quarterly to Overview & Scrutiny Committee |

| Objective | Planned actions | Timescales and milestones | Lead (desirable) | Targeted outcome | Resources | Reporting arrangements and frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Enforcement continued |  |  |  |  |  |  |
|  | 3.3 Vertex contract rebasing | Q1 & Q3 2006 | Policy & Compliance | - Establish 6 monthly Performance Review (Q1) - Adjust CSi charges in line with review outcomes (Q1) - Reengineer business to reflect outcomes - Support vertex relocation of services to Dingwall | Policy & Compliance Legal Vertex | Quarterly to Overview & Scrutiny Committee |
|  | 3.4 Improve payment recovery rate on responses to challenges which are not cancelled through improvements in quality. | Q4 2007 | Policy & Compliance | - Benchmark payment rates at pre-NtO, representations and appeals stage (Q1). - Implement quality improvement measures (Q2) (see objective 9.2) - Improve recovery rates by 5% at each stage of statutory process listed above. | Policy & Compliance | Monthly to Parking Board and Quarterly to Overview & Scrutiny Committee |
|  | 3.5 Reduce cancellation rates | Q2 2006 | Policy & Compliance | - Benchmark cancellation rates for PCNs cancelled PCNs (Q1) - Implement quality improvement measures (Q2) - Reduce PCNs cancelled by 5% | Policy & Compliance Vertex | Quarterly to Overview & Scrutiny Committee |

| Objective | Planned actions | Timescales and milestones | Lead (desirable) | Targeted outcome | Resources | Reporting arrangements and frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Kerbside |  |  |  |  |  |  |
| 4. On-Street Equipment | 4.2 Kerbside Space | Q3 2006 | Infrastructure Team | Investigate ways of quantifying usage and recommend other uses for kerbside space where occupancy is low e.g. motorcycle, disabled, leasing to local businesses etc. | Infrastructure Team | Quarterly to Overview & Scrutiny Committee |
| 5. Partnerships in Parking | 5.1 Joint Procurement Optimise the opportunity for cost reductions through joint procurement of equipment, systems and services in partnership with other Central London Boroughs. | See Targets | Service Development | 1 - Evaluate new on street equipment - joint testing and trialling with partners. Determine if equipment meets contract specification - By June 2006 2 - Prepare final business case for replacement of on street equipment and the use of alternative technologies for paid for parking on street - April 2006 3 - Seek necessary funding approvals and implement - from July 2006 Outcomes - reduce costs of maintenance and cash collection, increased revenues, reduced street clutter. | Infrastructure Team Service Development | Quarterly to Overview & Scrutiny Committee |
|  | 5.2 Harmonisation of controls (Exemplar – Project 4) | Q4 2007 | Service Development | Deliver at least 3 of the 6 identified projects throughout year. | Spread across 6 central London Boroughs and TfL. | PiP Project Board |
| 6. Permits & dispensations | 6.1 Business process re-engineering | Q3 2006 | Policy & Compliance | Reduction in number and complexity of different schemes. Simplified application and management processes. Cost savings to manage schemes. | Policy & Compliance Service Development | Quarterly to Overview & Scrutiny Committee |
|  | 6.2 Review of Resident permit on-street provision |  | Infrastructure Team | Increase/decrease number of spaces on street | Infrastructure Team |  |

| Objective | Planned actions | Timescales and milestones | Lead (desirable) | Targeted outcome | Resources | Reporting arrangements and frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Kerbside continued |  |  |  |  |  |  |
|  | 6.3 Respermit & Disabled fraud monitoring | Q2 – Q4 | Policy & Compliance | - Implement monitoring dashboard (Q1) - Explore options for using ANPR and CCTV capability - Target Fraud Team resources to prevent abuse of on-line respermit applications | Policy & Compliance | Quarterly to Overview & Scrutiny Committee |
| 7. Suspensions | 7.1 Suspension process re-engineering | Q3 2006 | Policy & Compliance | Simplified application and management processes, SLA developed and implemented, 30% of applications made on-line. | Policy & Compliance Service development IT | Quarterly to Overview & Scrutiny Committee |

| Offstreet |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 8. Off-Street | 8.1 Implementation of new contract | Q1 2006 | Car Parks / Service Development | Implement new car park management contract with CPS | Car Parks CPS | Monthly to Paring Board |
|  | 8.2 New barrier equipment installation | Q3 2006 | Car Parks / Service Development | Ensure that new equipment is installed at each Car Park to create a more efficient and effective network. | Car Parks CPS |  |
|  | 8.3 Credit and debit card payment contract | Q3 2006 | Car Parks – Sales and Marketing Team | Review and recommend changes to achieve Savings of 2% of credit card collection costs | Car Parks Finance | Quarterly to Overview & Scrutiny Committee |

| Objective | Planned actions | Timescales and milestones | Lead (desirable) | Targeted outcome | Resources | Reporting arrangements and frequency |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer Experience |  |  |  |  |  |  |  |  |
| 9. Internal view | 9.1 Extranet & Improving Partner communications | Ongoing | Customer Experience | Develop and improve quality & range of information Develop search functionality Roll-out site to other partners Better Management Information Online training Promotion to all areas of parking | IT Vertex NCP All Parking departments |  | Quarterly to Overview & Scrutiny Committee |  |
|  | 9.2 Improve quality of correspondence | Q2 2006 | Customer Experience / Policy & Compliance | 20% Reduction in comebacks Increased payment rates at all stages of the statutory process as linked to the incentive mechanism | Vertex |  | Monthly to Parking Board Quarterly to Overview & Scrutiny Committee |  |
|  | 9.3 Review handling of correspondence between Parking Services and Vertex | Q3 2006 | Customer Experience / Policy & Compliance | PCN challenges managed as BAU Identify and provide policy guidance as required | Vertex |  | Quarterly to Overview & Scrutiny Committee |  |
|  | 9.4 Centralisation of complaints | Q4 2007 | Customer Experience | Centralise all complaint handling through Customer Relations, including NCP/bailiff and other contractor complaints Improved customer experience Enhanced reputation of the Council | Vertex |  | Quarterly to Overview & Scrutiny Committee |  |
| 10. External view | 10.1 Customer research | Ongoing | Customer Experience | Increase knowledge of core customer groups; understand their specific needs regarding parking. Outcomes – improved Council image (City Survey) Improved customer experience | IT Market research agencies Communications One Stop Services Parking Services – All departments |  | Quarterly to Overview & Scrutiny Committee |  |
|  | 10.2 Local level consultation and liaison (e.g. with area forums) | Q2 2006/07 | AG | Develop and trial methodology for local level engagement to understand approach to local parking issues. | Customer Experience team |  | Output delivered as part of Cabinet. Member. Report. |  |

| Objective | Planned actions | Timescales and milestones | Lead (desirable) | Targeted outcome | Resources | Reporting arrangements and frequency |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer Experience continued |  |  |  |  |  |  |  |  |
|  | 10.3 Improve Perception of Parking - Promote the value of parking attendants and enforcement to the community |  | Policy & Compliance | - Engage directly with local businesses and residents through Area Forums, residents associations - Joint projects with City Guardians | Customer Experience |  | Quarterly to Overview & Scrutiny Committee |  |

| Team Management |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 11. Staff Development | 11.1 Review Staff Charter | Q1 & Q3 2006 | HD | 2 staff consultation meetings to review Staff Charter followed by revisions and release. | 1 officer from each team. | Parking Operational Management Team Bi-annual |
|  | 11.2 Improve IT training in department | Ongoing | HD | Series of informal departmental training sessions identified from needs analysis form. All staff to attend at least one training session. | Internally lead training. | Parking Operational Management Team Monthly |
|  | 11.3 Personal development | Q4 2007 | HD | All staff to have agreed personal development plans | All Parking Team | Reviewed quarterly with line manager |
|  | 11.4 Parking Managers | Q1 2006 Q4 2007 | HD | Determine baseline level required of training for Managers. All managers to attend training courses by end of financial year. | City Council Training Courses. | Parking Operational Management Team Monthly |
|  | 11.5 IIP accreditation | July 2006 October 2006 | HD | Gap Analysis of any shortfalls in the department to stop us from obtaining IIP accreditation. Depending on outcome of Gap analysis results apply for IIP accreditation or develop action plan to meet shortfalls. | HR | Parking Operational Management Team Monthly |

Appendix 3: Departmental Risk Register

| Risk No | Objective | Risk Owner | RAG Status | Vulnerability/ Cause | Consequences | Current Mitigation | Further Action Planned | Action Owner | Action Dates & Review Frequency | Target RAG Status | Independent Assurance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Parking system availability (ICPS) | Head of Parking Operations | Red | System architecture is not resilient and has not been delivered to specified requirements | System outages cause loss of data and/or productivity and ability to meet service levels | none | Changes to system planned as part of contractual requirements of 3rd party suppliers | Head of Parking Operations | May 2006 - progress reviewed fortnightly | Green | Audit |
| 2 | Bird Flu | Director of Parking | Red | Staff (and contractors staff) are unable to work | Enforcement levels not maintained, other works not completed | Implement Business Continuity Plan to reduce risk of contagion - Staff to work remotely where possible | 1. Identify and list key worker 2.Vaccinate key workers 3. Vaccinate all other staff | Director of Parking | 1. by April 2006 2 & 3. as required | Amber | None |
| 3 | Crossrail | Head of Parking Operations | Red | Works close streets | Residents parking places not available - residents vehicles displaced to other streets/zones causing knock on effect in surrounding areas - increased requirements for suspensions and removals/relocation of vehicles | none | Activity plan required from Crossrail against which mitigation activities can be planned. | Head of Parking Operations | June 2006 reviewed quarterly | Amber | Director of Transport |

| Risk No | Objective | Risk Owner | RAG Status | Vulnerability/ Cause | Consequences | Current Mitigation | Further Action Planned | Action Owner | Action Dates & Review Frequency | Target RAG Status | Independent Assurance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4 | Thames Water (and other utilities works) | Head of Parking Operations | Amber | Works close streets | Residents parking places not available - residents vehicles displaced to other streets/zones causing knock on effect in surrounding areas - increased requirements for suspensions and removals/relocation of vehicles | none | Activity plans required from Utility companies against which mitigation activities can be planned. | Head of Parking Operations | April 2006 reviewed quarterly | Green | Director of Transport |
| 5 | TfL - congestion Charge Western extension | Director of Parking | Amber | Extension to zone reduces number of vehicles entering Westminster | Reduction in On and Off street revenues | Challenge Congestion charge extension | None | Director of Parking | April 2006 reviewed quarterly | Amber | None |
| 6 | TfL - congestion Charge PTW (Powered Two Wheel Vehicle) extension | Director of Parking | Red | Reduces number of PTW's entering Westminster | Additional kerbside space is under utilised | Challenge Congestion charge extension | None | Director of Parking | April 2006 reviewed quarterly | Amber | None |
| 7 | Relocation of Vertex services to Dingwall | Head of Parking Operations | Red | Vertex relocate services to Dingwall | Loss of knowledge & experienced staff - reduced service levels and customer satisfaction | None | Set-up project team to assist, monitor and influence relocation plans and activities | Head of Parking Operations | April 2006 reviewed fortnightly | Green | Audit |